## Summary
| Course | CSC13002 – Nhập môn công nghệ phần mềm
| Class | 23CLC08
| Group | 2
PROJECT CONTRIBUTION
|  | Number of students working in the project | 5
|  | Number of tasks | 129
|  | Number of task hours | 382
|  | Number of Git commits | 11
|  | Max student percentage | 21%
|  | Project score | 10
Do not edit the grey cells. TAs will enter the score of all PAs in the project score and get the individual scores. Students can enter an estimated project score to see how percentages affects your scores
Use columns Tasks - Percent, Task Hours - Percent, Git - Percent as references for column Percent
No | Student ID | Full name | Tasks | Tasks - Percent | Task Hours | Task Hours - Percent | Git Commits | Git - Percent | Percent | Score - Student | Score - TA
1 | 23127488 | Lê Thị Minh Thư | 29 | 22.48% | 84 | 21.99% | 2 | 18.18% | 19.5% | 9.5
2 | 23127361 | Thạch Ngọc Hân | 25 | 19.38% | 76 | 19.9% | 2 | 18.18% | 20% | 9.5
3 | 23127406 | Nguyễn Tấn Lộc | 25 | 19.38% | 77 | 20.16% | 2 | 18.18% | 20% | 9.5
4 | 23127203 | Trần Hữu Khang | 26 | 20.16% | 74 | 19.37% | 2 | 18.18% | 19% | 9
5 | 23127460 | Lê Đình Minh Quân | 24 | 18.6% | 71 | 18.59% | 3 | 27.27% | 21% | 10

## Tasks
A task should be done by only 1-2 students. Duplicate tasks are not recommended Each member should work on at least 5 tasks
No | Student ID | Full name | Task Description | Hours | Evidence (screenshots of chat messages, of Git commits... proving that you perform and finish the task)
1 | 23127488 | Lê Thị Minh Thư | Complete the project description [PA0] | 2 | Minh chứng contribute: PROOF FOR WORKING
2 | 23127361 | Thạch Ngọc Hân | Prepare questions for tomorrow meeting [PA0] | 2
3 | 23127406 | Nguyễn Tấn Lộc | Complete the team contract [PA0] | 3
4 | 23127203 | Trần Hữu Khang | Complete the team contract [PA0] | 3
5 | 23127460 | Lê Đình Minh Quân | Prepare questions for tomorrow meeting [PA0] | 2
6 | 23127488 | Lê Thị Minh Thư | Complete project proposal [PA0] | 2
7 | 23127361 | Thạch Ngọc Hân | Complete project proposal [PA0] | 2
8 | 23127406 | Nguyễn Tấn Lộc | Initialize a web project | 3
9 | 23127203 | Trần Hữu Khang | Complete timeline | 3
10 | 23127460 | Lê Đình Minh Quân | Initialize a web project | 2
11 | 23127488 | Lê Thị Minh Thư | Project vision [PA1] | 4
12 | 23127361 | Thạch Ngọc Hân | Project introduction for RUP [PA1] | 3
13 | 23127406 | Nguyễn Tấn Lộc | Project organization for RUP [PA1] | 3
14 | 23127203 | Trần Hữu Khang | Project monitoring and control for RUP [PA1] | 3
15 | 23127460 | Lê Đình Minh Quân | Project overview for RUP [PA1] | 2
16 | 23127488 | Lê Thị Minh Thư | Research about use-case diagrams [PA2] | 2
17 | 23127361 | Thạch Ngọc Hân | Research about use-case diagrams. [PA2] | 2
18 | 23127406 | Nguyễn Tấn Lộc | Research about use-case diagrams. [PA2] | 2
19 | 23127203 | Trần Hữu Khang | Finish the project plan in RUP. [PA2] | 2
20 | 23127460 | Lê Đình Minh Quân | Research about use-case diagrams. [PA2] | 2
21 | 23127488 | Lê Thị Minh Thư | Writing “Rate Article” Use-Case Specification [PA2] | 3
22 | 23127361 | Thạch Ngọc Hân | Writing “Save Article to Favourite” Use-case Specification [PA2] | 3
23 | 23127406 | Nguyễn Tấn Lộc | Writing “Submit Article” Use-case Specification [PA2] | 3
24 | 23127203 | Trần Hữu Khang | Write Use-Case Specification for “View Recommended Articles” [PA2] | 3
25 | 23127460 | Lê Đình Minh Quân | Draw a Gantt Chart for the Plan in PA1 + Complete Section 4 in RUP. [PA2] | 4
26 | 23127488 | Lê Thị Minh Thư | Writing “Search Article” Use-Case Specification. [PA2] | 3
27 | 23127361 | Thạch Ngọc Hân | Writing “View Reading History” Use-case Specification [PA2] | 3
28 | 23127406 | Nguyễn Tấn Lộc | Writing “Comment Article” Use-case Specification [PA2] | 3
29 | 23127203 | Trần Hữu Khang | Write Use-Case Specification for “Generate Reports” [PA2] | 3
30 | 23127460 | Lê Đình Minh Quân | Writing “Log out” Use-Case Specification [PA2] | 3
31 | 23127488 | Lê Thị Minh Thư | Adjust and finish all the remaining parts in the Vision [PA2] | 2
32 | 23127361 | Thạch Ngọc Hân | Adjust and finish all the remaining parts in the Vision. [PA2] | 3
33 | 23127406 | Nguyễn Tấn Lộc | Writing “Read Article” Use-case Specification [PA2] | 3
34 | 23127203 | Trần Hữu Khang | Write Use-Case Specification for “Manage User Roles” [PA2] | 3
35 | 23127460 | Lê Đình Minh Quân | Writing “Check Plagiarism” Use-Case Specification. [PA2] | 3
36 | 23127488 | Lê Thị Minh Thư | Writing “Share Article” Use-Case Specification [PA2] | 3
37 | 23127361 | Thạch Ngọc Hân | Writing View Statics Use-case specification [PA2] | 3
38 | 23127406 | Nguyễn Tấn Lộc | Writing “Log in” Use-case Specification [PA2] | 3
39 | 23127203 | Trần Hữu Khang | Write Use-Case Specification for “Manage Articles” [PA2] | 3
40 | 23127460 | Lê Đình Minh Quân | Writing “Verify MFA Code ” Use-case Specification [PA2] | 3
41 | 23127488 | Lê Thị Minh Thư | Draw Use Case Model. [PA2] | 3
42 | 23127361 | Thạch Ngọc Hân | Writing Filter Articles Use-case specification [PA2] | 3
43 | 23127406 | Nguyễn Tấn Lộc | Writing “Resign” Use-case Specification [PA2] | 3
44 | 23127203 | Trần Hữu Khang | Write Use-Case Specification for “Create Article [PA2] | 3
45 | 23127460 | Lê Đình Minh Quân | Draw Use Case Model. [PA2] | 4
46 | 23127488 | Lê Thị Minh Thư | Writing “Change Password” Use-Case Specification [PA2] | 3
47 | 23127361 | Thạch Ngọc Hân | Writing Recover Password Use-case specification [PA2] | 3
51 | 23127488 | Lê Thị Minh Thư | Write Introduction for SAD [PA3] | 2
52 | 23127488 | Lê Thị Minh Thư | Write Architecture Goals and Constraints [PA3] | 2
53 | 23127488 | Lê Thị Minh Thư | Redraw Use-Case Model [PA3] | 2
54 | 23127203 | Trần Hữu Khang | Add document identifier for use-case documents. [PA3] | 2
55 | 23127488 | Lê Thị Minh Thư | Draw and Descript for Logical View. [PA3] | 3
56 | 23127361 | Thạch Ngọc Hân | Overview of Model Component [PA3] | 3
57 | 23127406 | Nguyễn Tấn Lộc | Overview of Routes Component [PA3] | 3
58 | 23127203 | Trần Hữu Khang | Overview of Controller Component [PA3] | 2
59 | 23127460 | Lê Đình Minh Quân | Overview of View (UI) Component [PA3] | 2
60 | 23127406 | Nguyễn Tấn Lộc | Draw a Class-Diagram and Write a Description for: -​ View component: Authentication: View Login Page [PA3] | 3
61 | 23127406 | Nguyễn Tấn Lộc | Draw a Class-Diagram and Write a Description for: ​ View component: Authentication: View Error Page [PA3] | 3
62 | 23127406 | Nguyễn Tấn Lộc | Draw a Class-Diagram and Write a Description for: -​ View component: Authentication View Register Page [PA3] | 3
63 | 23127406 | Nguyễn Tấn Lộc | Draw a Class-Diagram and Write a Description for: -​ View component: Authentication View Forgot Password [PA3] | 3
64 | 23127203 | Trần Hữu Khang | Draw a Class-Diagram and Write a Description for : - View component: Navigation Bar [PA3] | 3
65 | 23127203 | Trần Hữu Khang | Draw a Class-Diagram and Write a Description for: View component: Footer [PA3] | 3
66 | 23127203 | Trần Hữu Khang | Draw a Class-Diagram and Write a Description for: View component: Editor View [PA3] | 3
67 | 23127460 | Lê Đình Minh Quân | Draw a Class-Diagram and Write a Description for: View component: HomePage [PA3] | 3
68 | 23127460 | Lê Đình Minh Quân | Draw a Class-Diagram and Write a Description for: -​ View component: Admin View [PA3] | 3
69 | 23127361 | Thạch Ngọc Hân | Draw a Class-Diagram and Write a Description for: View component:Article Detail [PA3] | 3
70 | 23127361 | Thạch Ngọc Hân | Draw a Class-Diagram and Write a Description for: View component: User Profile View. [PA3] | 3
71 | 23127361 | Thạch Ngọc Hân | Draw a Class-Diagram and Write a Description for: ​ View component: Comment Section [PA3] | 3
72 | 23127488 | Lê Thị Minh Thư | Draw a Class-Diagram and Write a Description for: View component: Search Article View [PA3] | 3
73 | 23127488 | Lê Thị Minh Thư | Draw a Class-Diagram and Write a Description for: View component: Dashboard View [PA3] | 3
74 | 23127488 | Lê Thị Minh Thư | Draw a Class-Diagram and Write a Description for: View component: Writer view. [PA3] | 3
75 | 23127203 | Trần Hữu Khang | Draw a Class-Diagram and Write a Description for: Model component: Writer [PA3] | 3
76 | 23127203 | Trần Hữu Khang | Draw a Class-Diagram and Write a Description for: Model component: User [PA3] | 3
77 | 23127460 | Lê Đình Minh Quân | Draw a Class-Diagram and Write a Description for: Model component: Editor [PA3] | 3
78 | 23127460 | Lê Đình Minh Quân | Draw a Class-Diagram and Write a Description for: Model component: Admin [PA3] | 3
79 | 23127406 | Nguyễn Tấn Lộc | Draw a Class-Diagram and Write a Description for: Model component: Tag [PA3] | 3
80 | 23127406 | Nguyễn Tấn Lộc | Draw a Class-Diagram and Write a Description for: Model component: Category [PA3] | 3
81 | 23127361 | Thạch Ngọc Hân | Draw a Class-Diagram and Write a Description for: Model component: Comment [PA3] | 3
82 | 23127488 | Lê Thị Minh Thư | Draw a Class-Diagram and Write a Description for: Model Component: Article [PA3] | 3
83 | 23127203 | Trần Hữu Khang | Draw a Class-Diagram and Write a Description for: Controller component: Authentication Controller [PA3] | 3
84 | 23127460 | Lê Đình Minh Quân | Draw a Class-Diagram and Write a Description for: Controller component:User Controller [PA3] | 3
85 | 23127460 | Lê Đình Minh Quân | Draw a Class-Diagram and Write a Description for: Controller component:Admin Controller [PA3] | 3
86 | 23127406 | Nguyễn Tấn Lộc | Draw a Class-Diagram and Write a Description for: Controller component Writer Controller [PA3] | 3
87 | 23127361 | Thạch Ngọc Hân | Draw a Class-Diagram and Write a Description for: Controller component: Comment Controller [PA3] | 3
88 | 23127361 | Thạch Ngọc Hân | Draw a Class-Diagram and Write a Description for: Controller component Editor Controller [PA3] | 3
89 | 23127488 | Lê Thị Minh Thư | Draw a Class-Diagram and Write a Description for: Controller component: Article Controller [PA3] | 3
90 | 23127488 | Lê Thị Minh Thư | Draw a Class-Diagram and Write a Description for: Controller component: Search Controller [PA3] | 3
91 | 23127488 | Lê Thị Minh Thư | Draw a Class-Diagram and Write a Description for: Controller component: Dashboard Controller [PA3] | 3
92 | 23127203 | Trần Hữu Khang | Render Class Diagram [PA3] | 4
93 | 23127460 | Lê Đình Minh Quân | Scripting and synthesising code format for coherent Class Diagram rendering [PA3] | 4
94 | 23127361 | Thạch Ngọc Hân | Validate the whole architecture document. [PA3] | 3
95 | 23127406 | Nguyễn Tấn Lộc | Validate the whole architecture document. [PA3] | 3
96 | 23127488 | Lê Thị Minh Thư | Complete Deployment from PA3 [PA4] | 4
97 | 23127361 | Thạch Ngọc Hân | Complete Deployment from PA3 [PA4] | 4
98 | 23127406 | Nguyễn Tấn Lộc | Revise the SAD document [PA4] | 3
99 | 23127203 | Trần Hữu Khang | Revise the SAD document [PA4] | 2
100 | 23127460 | Lê Đình Minh Quân | Complete Implementation View from PA3 [PA4] | 4
101 | 23127488 | Lê Thị Minh Thư | Design Prototype Respective to your Use-Case in PA2 | 3
102 | 23127361 | Thạch Ngọc Hân | Design Prototype Respective to your Use-Case in PA2 | 3
103 | 23127406 | Nguyễn Tấn Lộc | Design Prototype Respective to your Use-Case in PA2 | 3
104 | 23127203 | Trần Hữu Khang | Design Prototype Respective to your Use-Case in PA2 | 3
105 | 23127460 | Lê Đình Minh Quân | Design Prototype Respective to your Use-Case in PA2 | 3
106 | 23127488 | Lê Thị Minh Thư | Fill in the UI and write a description for the sections: Authentication [PA4] | 3
107 | 23127361 | Thạch Ngọc Hân | Fill in the UI and write a description for the sections: Article [PA4] | 3
108 | 23127406 | Nguyễn Tấn Lộc | Fill in the UI and write a description for the sections: Rating [PA4] | 3
109 | 23127203 | Trần Hữu Khang | Fill in the UI and write a description for the sections: Admin [PA4] | 3
110 | 23127460 | Lê Đình Minh Quân | Fill in the UI and write a description for the sections: Favourites [PA4] | 3
111 | 23127488 | Lê Thị Minh Thư | Fill in the UI and write a description for the sections: HomePage [PA4] | 3
112 | 23127361 | Thạch Ngọc Hân | Fill in the UI and write a description for the sections: Comment [PA4] | 3
113 | 23127406 | Nguyễn Tấn Lộc | Fill in the UI and write a description for the sections: Account [PA4] | 3
114 | 23127203 | Trần Hữu Khang | Fill in the UI and write a description for the sections: History [PA4] | 3
115 | 23127460 | Lê Đình Minh Quân | Fill in the UI and write a description for the sections: Article Reviewer [PA4] | 3
116 | 23127488 | Lê Thị Minh Thư | Fill in the UI and write a description for the sections: Search [PA4] | 3
117 | 23127361 | Thạch Ngọc Hân | Fill in the UI and write a description for the sections: Writer [PA4] | 3
118 | 23127406 | Nguyễn Tấn Lộc | Fill in the UI and write a description for the sections: Editor [PA4] | 3
119 | 23127203 | Trần Hữu Khang | Fill in the UI and write a description for the sections: Share [PA4] | 3
120 | 23127488 | Lê Thị Minh Thư | Write Test Plan [PA5] | 3
121 | 23127460 | Lê Đình Minh Quân | Write Test Plan [PA5] | 3
122 | 23127488 | Lê Thị Minh Thư | Wrtite Test Cases : Feature: SEARCH [PA5] | 3
123 | 23127361 | Thạch Ngọc Hân | Wrtite Test Cases : Feature: FILTER [PA5] | 3
124 | 23127406 | Nguyễn Tấn Lộc | Wrtite Test Cases : Feature: READ ARTICLE [PA5] | 3
125 | 23127460 | Lê Đình Minh Quân | Wrtite Test Cases : Feature: CREATE ARTICLE [PA5] | 3
126 | 23127203 | Trần Hữu Khang | Wrtite Test Cases : Feature: VIEW STATISTICS[PA5] | 3
127 | 23127460 | Lê Đình Minh Quân | Wrtite Test Report [PA5] | 3
128 | 23127361 | Thạch Ngọc Hân | Write Content for Presentation [PA5] | 6
129 | 23127488 | Lê Thị Minh Thư | Write Content for Presentation [PA5] | 5
130 | 23127406 | Nguyễn Tấn Lộc | Revise, Summary and Complete Project Contribution. [PA5] | 6
131 | 23127203 | Trần Hữu Khang | Revise, Summary for PROOF FOR WORKING. [PA5] | 3
132 | 23127203 | Trần Hữu Khang | Weekly Report [PA5] | 2